## Project Overall
Mini environmental monitoring station with module LCD display using I2C module and can alert with buzzer when certain conditions are met, sent data measured to phone UART app via Bluetooth with UART communication (module HC-05). The station use mcu stm32f103c8t6 aka blue pill that can measure real-time temperature & humidity (module DHT11), gas (module MQ2), and can display them on the lcd screen. The device also has 2 button, 1 to snooze the alarm, 1 to change the display mode in cycle.

## Tasks management
Nhiệm vụ | Yêu cầu | Ngày giao việc | Hạn chót | Người phụ trách | Tình trạng | Đạt yêu cầu? | Ghi chú | Cột 8
Chốt đề tài Environment Station | Biểu diễn tổng quan các chức năng, nguyên lý hoạt động | 2026-01-16 | 2026-01-16 | Vinh, Ân, Dũng | Đúng hạn | TRUE | Bước đầu thành công, xuất phát sớm | Giai đoạn 1 - 0%
Viết Functional & Non-Functional requirement | Trình bày được đặc tả hệ thống Functional và Non-Functional rõ ràng, đầy đủ như mong muốn ban đầu, đúng lý thuyết Thầy Bảo dạy | 2026-01-17 | 2026-01-17 | Dũng | Đúng hạn | FALSE | Các mô tả chưa có tính cụ thể, một số chưa đúng với mô tả hệ thống ban đầu đã thống nhất. Cần chỉnh sửa lại, đánh giá cao sự đúng hạn
Chỉnh sửa Functional & Non-Functional requirement | Chỉnh lại FRs và NFRs với đúng kỳ vọng ban đầu và đúng chuẩn được dạy ở lớp | 2026-01-17 | 2026-01-17 | Vinh, Ân | Đúng hạn | TRUE
Viết System specification | Mô tả các component sử dụng để chạy hệ thống, cách kết nối, mode sử dụng của các modules | 2026-01-17 | 2026-01-19 | Vinh | Đúng hạn | TRUE
Họp và đánh giá lại 2 bước trên, góp ý chỉnh sửa | Chốt đề tài và làm rõ một số ý chưa thống nhất | 2026-01-21 | 2026-01-21 | Vinh, Ân, Dũng | Đúng hạn | TRUE | Đưa vào thêm một số chức năng mới, hiển thị lcd, đo nồng độ khí ga, gửi uart
Chỉnh lại Requirement và Specification | Sửa lại theo mô tả hệ thống đã thống nhất | 2026-01-21 | 2026-01-22 | Vinh | Đúng hạn | TRUE
Tìm hiểu DHT11 MQ2 LCD-I2C | Tìm hiểu cách hoạt động và hướng dẫn cho Vinh cách sử dụng | 2026-03-02 | 2026-03-04 | Dũng | Đúng hạn | FALSE | Đánh giá cao sự đúng hạn nhưng còn sơ sài, chatgpt . Vinh phải tự tìm hiểu sau đó
Vẽ schematic - Block diagram | Vẽ block diagram theo chuẩn được dạy | 2026-03-08 | 2026-03-15 | Vinh | Đúng hạn | TRUE
Vẽ schematic - Power tree | Vẽ power tree theo chuẩn, ghi rõ công suất và cường độ dòng từng linh kiện tiêu thụ | 2026-03-08 | 2026-03-15 | Vinh | Đúng hạn | TRUE
Vẽ schematic - Thermal check table | Thêm bảng đo nhiệt độ khi hoạt động, tạo sự nổi bật | 2026-03-08 | 2026-03-15 | Ân | Đúng hạn | TRUE |  | Giai đoạn 2 - 50%
Vẽ schematic - Power supply | Thiết kế bộ nguồn gồm LM2596, AMS1117 và các linh kiện vệ tinh để cấp power rail cho mạch | 2026-03-15 | 2026-03-22 | Ân | Đúng hạn | TRUE | Đầy đủ các khối, các linh kiện vệ tinh chưa đúng, validate còn lỗi
Vẽ schematic - Main system | Thiết kế các khối xử lý trung tâm: MCU Bluepill, Button driver, Sensors, LCD I2C, 2 Uart, Buzzer,... và các trở, tụ, xung quanh | 2026-03-15 | 2026-03-22 | Vinh | Đúng hạn | TRUE | Đày đủ các khối chức năng, validate còn lỗi, một số linh kiện chưua có footprint, đợi feedback từ thầy'
Sửa lỗi Power tree | Sửa sau khi nghe feedback thầy Bảo và validate còn 20 lỗi | 2026-03-23 | 2026-03-26 | Ân | Đúng hạn | TRUE | Đã ổn, đúng với datasheet ban đầu
Sửa lỗi Main system | Sửa sau khi nghe feedback thầy Bảo và validate còn 40 lỗi | 2026-03-23 | 2026-03-26 | Vinh | Đúng hạn | TRUE | Hết lỗi, đã chỉnh lại theo feedbackl
Vẽ các component không có trên Altium, vẽ tay | HC-05, MQ-2, một số linh kiện không có trong thư viện, yêu cầu phải vẽ symbol và footprint manually | 2026-03-23 | 2026-03-26 | Vinh | Đúng hạn | TRUE | Gắn header và chỉnh lại mode I/O của các linh kiện
Vẽ PCB Layout | Schematic đã được hoàn thiện và sửa hết lỗi, vẽ layout | 2026-03-26 | 2026-03-26 | Ân | Đúng hạn | TRUE | Đánh giá cao sự hardcore làm trong 1 ngày
Tổng hợp, upload lên github | Up tất cả tài liệu tiến độ hiện tại lên github để Dũng làm report | 2026-03-27 | 2026-03-27 | Vinh | Đúng hạn | TRUE
Làm report 50% | Làm report theo yêu cầu của Thầy ghi rõ trong slide: The report must be written following the embedded system design process | 2026-03-27 | 2026-03-30 | Dũng | Đúng hạn | FALSE | Dũng làm ổn, khung sườn cover gần đủ nhưng vẫn còn thiếu vài bước theo quy trình TKHTN, lấy sai hình cho report
Vẽ proteus để simulate | Vẽ lại toàn bộ hệ thống trên proteus dựa trên schematic altium và simulate, đi dây lại để phù hợp với mô phỏng | 2026-04-01 | 2026-04-02 | Vinh | Đúng hạn | TRUE | Đã vẽ lại hoàn chỉnh, project simulate được
Code stm32cubeide | Code firmware cho toàn bộ hệ thống, debug cho từng khối một và build lên từ từ, vừa code vừa mô phỏng để đảm bảo behave đúng | 2026-04-02 | 2026-04-11 | Vinh | Đúng hạn | FALSE | Tất cả các linh kiện đã chạy đúng trừ LCD chưa giao tiếp I2C được dù đã thử các địa chỉ 0x20 x27 x3F x3E và sử dụng code dò địa chỉ, DHT11 đọc sai số do các bit cuối dọc bị lệch cần phải test trên breadboard
Sửa lại report 50% | Làm report theo yêu cầu của Thầy ghi rõ trong slide: The report must be written following the embedded system design process | 2026-03-30 | 2026-04-09 | Dũng | Đúng hạn | FALSE | Đã ổn hơn lần trước, thêm được 5 đoạn nội dung ở đầu mỗi phần,, vẫn còn lấy hình sai
In PCB | In 5 mạch |  | 2026-04-05 | Ân | Đúng hạn | TRUE | Ân ứng tiền 190k
Làm lại báo cáo công việc trên excel | Viết lại biên bản làm việc rõ ràng và phân nhiệm vụ mới | 2026-04-11 | 2026-04-12 | Vinh | Đúng hạn | TRUE |  | Giai đoạn 3 - 100%
Mua linh kiện điện tử | Mua tất cả linh kiện điện tử cần để lắp mạch breadboard: HC05, MQ2, DHT11, LCD PCF, Breadboard, LM2596, AMS1117, dây... | 2026-04-11 | 2026-04-12 | Vinh | Đúng hạn | TRUE | Tổng bill 296k, vinh ứng
Làm report 100% | Viết một bản report hoàn chỉnh "The report must be written following the embedded system design process", bao gồm quá trình trong các slide bài giảng từ đầu đến cuối. Trình bày kĩ và đầy đủ nội dung mà team đã làm từ đầu đến cuối, viết thêm các phần lý thuyết để nộp. | 2026-04-12 | Sáng 24/04/2026 | Dũng | Đúng hạn | TRUE | Các tài liệu: https://docs.google.com/document/d/1ozNgph806v6iIgOBkZLcseK3Fe_vgAtyg2jRV2a9toI/edit?usp=sharing | Guideline: https://docs.google.com/document/d/1vAiog7G-fEwVRg1F-I0hjbZN5FIbIZKtpWRS2lV4W_4/edit?usp=sharing
Làm slide | Làm slide để thuyết trình 50% | 2026-04-12 | 2026-04-20 | Ân | Đúng hạn | TRUE | Ổn nhưng cần bổ sung chỉnh sửa
Sửa slide | Chỉnh lại slide thuyết trình 50%, làm rõ một số điểm và lược bớt những nội dung không cần thiết. | 2026-04-20 | 2026-04-20 | Vinh | Đúng hạn | TRUE
Thuyết trình | Thuyết trình 50% | 2026-04-12 | 2026-04-20 | Vinh | Đúng hạn | TRUE
Lắp mạch breadboard | Lắp lại hệ thống lên breadboard, có thể giống với sơ đồ trong proteus hay altium, tùy thuộc vào điều kiện thực tế. Mục tiêu là để thỏa mãn các yêu cầu ban đầu của hệ thống | 2026-04-12 | 2026-04-27 | Vinh | Đúng hạn | TRUE | Debug thành công lỗi hiển thị lcd
Sửa report 100% | Chỉnh sửa lại report nếu cần | 2026-04-20 | 27/04 (extend10/05) | Vinh, Dũng | Đúng hạn | TRUE | kéo dài đến 10/05
Nạp code lên breadboard và debug lại | Debug trên mạch breadboard để sửa 2 lỗi: chưa hiển thị được LCD, và đọc DHT11 chưa chính xác | 2026-04-20 | 2026-04-26 | Vinh | Đúng hạn | TRUE
Hoàn thiện sản phẩm trên breadboard 100% | Lắp driver cho buzzer, gửi bluetooth qua điện thoại bằng jdy 31 | 2026-04-27 | 2026-05-09 | Vinh | Đúng hạn | TRUE | Xong
Update github | Update lại trên github tiến độ sau khi hoàn thành | 2026-04-27 | 2026-04-27 | Vinh | Đúng hạn | TRUE
Làm slide thuyết trình 100% |  | 2026-05-09 | 2026-05-11 | Vinh, Ân | Đúng hạn | TRUE
Thuyết trình 100% | Thuyết trình 100% | 2026-05-11 | 2026-05-11 | Vinh | Đúng hạn | TRUE
[5 empty] | Đang làm | FALSE
[5 empty] | Đang làm | FALSE
[5 empty] | Đang làm | FALSE
[5 empty] | Đang làm | FALSE
[5 empty] | Đang làm | FALSE
[5 empty] | Đang làm | FALSE
[5 empty] | Đang làm | FALSE

## Requirement definition
Functional Requirements
| Level 1 | Level 2 | Level 3
Environmental sensing | The system shall acquire environmental measurements. | The system shall measure ambient temperature. | Temperature shall be reported in °C.
|  | The system shall measure indoor relative humidity. | Humidity shall be reported in %RH.
|  | The system shall measure indoor gas/smoke level. | Gas/smoke level shall be reported as ppm
User interaction and alerting | The device shall be able to interact with the user | The device should notify the user when certain thresholds are reached | An audible alarm shall activate when humidity is > 60%RH or < 30%RH.
An audible alarm shall activate when gas/smoke level exceeds 800 ppm.
|  | The system shall allow the user to acknowledge (silence) an active alarm. | A user input action shall silence the alarm when pressed.
|  | The device should have a button to display data on demand. | Each press shall cycle display modes in a fixed order: First press display only temperature, second press displays only humidity, third press display only gas density, fourth press displays all three properties.
|  | The system shall allow the user to enable/disable mobile data transmission. | Each press shall switches between enable and disable mobile data transmission
Local display | The system shall present measured information locally. | The system shall display temperature with label and unit. | The message displayed should be in a fixed frame : "Temp:XX.X*C".
|  | The system shall display humidity with label and unit. | The message displayed should be in a fixed frame : "Humidity:XX.X%RH".
|  | The system shall display gas/smoke level with label and unit. | The message displayed should be in a fixed frame : "Gas density:XX.Xppm".
Mobile data reporting | The system shall provide measured information to the user remotely. | The system shall transmit temperature, humidity, and gas/smoke level to a mobile app over Bluetooth | The transmitted data shall include Temp, Humidity, Gas fields.
The message sent should be in a fixed frame : "The temp is XX.X*C, The humidity is XX.X%RH, The gas density is XX.Xppm".
Non-Functional Requirements
| Level 1 | Level 2 | Level 3
Usability | The system shall be easy to use for non-technical users. | Simple UI: The system shall provide simple user interaction. | The system shall use ≤ 2 buttons for user control (e.g., Display mode, Alarm acknowledge).
|  | Readability: The system shall present values clearly. | Text on LCD shall be readable at 30–50 cm viewing distance.
| The system shall meet basic electrical safety for a desktop device. | Electrical safety: The system shall not expose hazardous voltages to the user. | User-accessible parts shall operate at ≤ 5 V DC (or be fully enclosed).
|  | Thermal safety: The system shall not become dangerously hot in normal use. | Enclosure surface temperature shall be < 50 °C during operation.
| The system shall be low-cost. | Total hardware cost shall be ≤ 250,000 VND.
| The system shall be compact for desktop use. | Size: The enclosure shall fit within 20 cm × 10 cm × 10cm.
Mass: Total mass shall be ≤ 300g.
Environmental operating conditions (Durability) | The system shall operate reliably in indoor environments. | Temperature: The system shall operate from 0 to 40 °C (typical indoor).
Humidity: The system shall operate at 20–80%RH non-condensing.
Reliability / Availability | The system shall run continuously with minimal failures. | Continuous operation: The system shall operate continuously for ≥ 24 hours without manual reset.
Fault recovery: If a sensor read fails, the system shall continue running and show an error indicator.
Software robustness: The system shall include a watchdog reset or equivalent mechanism to recover from firmware hang.
Performance | The system shall provide timely updates and alerts. | The system shall provide timely sensor update rate | Temperature shall update at least once every 10 s.
Humidity shall update at least once every 10–20 s.
Gas/smoke level shall update at least once every 5 s.
Display update: LCD shall refresh at least once every 1 s or when the displayed value changes.
Alert latency: Alarm shall activate within ≤ 5 s after threshold violation is detected.
| The system shall have low power consumption. | Average power: Average power consumption shall be ≤ (choose target).
Peak current: Peak current shall be ≤ (choose) to avoid brownout
| The system shall support the selected power source. | The system shall operate from an external power sourse 5 V supply.
Respect Dung Ho's effort.
DUNG HO
|  | Level 1 | Level 2 | Level 3
| Topic | Level 1 – Stakeholder | Level 2 – Technical | Level 3 – Detailed Functional
| Environmental monitoring | The device should help users monitor indoor environmental conditions. | The system shall measure temperature, humidity, and gas levels in real time. | The system shall obtain data from LM35, DHT11, and MQ-2 at each sampling cycle.
| Temperature | The device should provide information about indoor temperature. | The system shall measure temperature. | The system shall read temperature from LM35 via an ADC pin of STM32F103C8T6.
| Humidity | The device should provide information about indoor humidity. | The system shall measure humidity. | The system shall read humidity from DHT11 via a digital GPIO pin.
| Gas detection | The device should detect dangerous gas or smoke conditions. | The system shall measure gas concentration. | The system shall read gas level from MQ-2 via an analog input of STM32.
| LCD display | The device should display environmental information clearly. | The system shall display temperature, humidity, and gas on an LCD. | The system shall send formatted sensor data to the LCD via I2C.
| Local alert | The device should warn users locally when conditions are unsafe. | The system shall activate a buzzer when thresholds are exceeded. | The system shall drive a digital pin of STM32 to activate the buzzer.
| Remote monitoring | Users should receive data and alerts on their phone. | The system shall send data and alerts to Blynk via Wi-Fi. | The system shall transmit sensor values to Blynk through a UART Wi-Fi module using a Blynk token.
|  | Level 1 | Level 2 | Level 3
| Topic | Level 1 – Stakeholder | Level 2 – Technical | Level 3 – Detailed Non-Functional
| Sampling rate (Performance) | The system should respond in near real time. | The system shall operate with a defined sampling rate. | The system shall sample each sensor at least once every 1 second.
| LCD refresh (Performance) | The display should look smooth and updated. | The LCD shall update regularly. | The LCD shall refresh displayed values at least every 1 second.
| Local alert latency (Performance) | The alarm should sound quickly in danger. | The local alert shall activate promptly after threshold violation. | The buzzer shall activate within 1 second after a threshold is exceeded.
| Cloud update rate (Performance) | Data on the phone should be reasonably fresh. | The system shall send data to Blynk periodically. | The system shall upload data to Blynk at least every 2 seconds.
| Notification delay (Performance) | Phone alerts should arrive quickly. | The system shall send timely notifications. | Blynk notifications shall reach the phone within 5 seconds after violation.
| Reliability | The device should work continuously without crashing. | The system shall operate reliably during normal use. | The system shall run for at least 8 hours continuously without manual reset.
| Size / Form factor | The device should be suitable for desktop use. | The system shall have a compact physical design. | The enclosure shall fit within a typical desktop footprint (small form factor).
safety
lowcost
simple userinterface

## System specification
System Requirements (Hardware component requirements)
The monitoring station shall function as a desktop environmental monitoring device with local display, audible alarm, and Bluetooth reporting. | Power and Regulation System | The system shall accept 9 V DC input from a 2 A adapter as the main power source.
The system shall use an LM2596 buck converter to generate a regulated 5 V DC output.
The LM2596 output shall be set to 5.0 V ± 5% under normal operating load.
The 5 V rail shall supply the MCU board and all peripherals used in the system.
The power subsystem shall provide a common ground shared by all modules.
| Processing and Control System | The system shall use an STM32F103C8T6 (Blue Pill) as the centralized controller for sensing, display, alarm, and communication.
The MCU subsystem shall operate from the 5 V rail and internally provide 3.3 V logic for MCU I/O.
The MCU shall provide: 1 I2C interface for the LCD module 1 UART interface for the HC-05 module Digital GPIO inputs for DHT11, and 2 buttons, Analog input ADC for MQ2 AO Digital GPIO output for buzzer control
| Temperature Sensing Subsystem | The system shall use an DHT11 module to measure ambient temperature.
The LM35 output shall be connected to an STM32 ADC input.
| Humidity Sensing Subsystem | The system shall use a DHT11 module to measure indoor relative humidity.
The DHT11 shall interface to the MCU using a single digital data GPIO line.
| Gas/Smoke Detection Subsystem | The system shall use an MQ2 module to detect indoor gas/smoke level.
The MQ2 shall connect to the MCU using its Analog output (AO) pin.
The MQ2 module threshold shall be adjusted such that AO becomes active at the project alarm threshold equivalent (gas/smoke > 800 ppm)
The system shall use the MQ2 AO state to trigger an alarm condition.
| Local Display Subsystem | The system shall use a 16×2 LCD with I2C backpack to display measured values.
The LCD shall communicate with the MCU through I2C (SCL, SDA).
The I2C electrical interface shall be compatible with 3.3 V MCU I/O levels (use 3.3 V pull-ups or level shifting if the LCD backpack pulls up to 5 V).
| Audible Alarm Subsystem | The system shall use an active buzzer 3.3v to provide audible alerts.
The buzzer shall be controlled by the MCU using a digital GPIO output (ON/OFF control).
The buzzer shall activate when: humidity is > 60%RH or < 30%RH; or MQ2 DO indicates gas/smoke exceeds the configured threshold equivalent to > 800 ppm.
| Wireless Communication | The system shall use an HC-05 Bluetooth module for wireless transmission to a phone UART app.
The HC-05 shall interface with the MCU using UART TX/RX.
The system shall transmit temperature, humidity, and gas/smoke information in a fixed message structure.
The UART logic levels shall be compatible with 3.3 V MCU I/O (no 5 V logic driving into HC-05 RX).
| User Input (2 Buttons) | The system shall include 2 push buttons connected to MCU GPIO inputs.
Button 1 shall toggle Bluetooth transmission enable/disable.
Button 2 shall cycle LCD display modes in the fixed order: Temperature → Humidity → Gas/Smoke → All.
The system shall implement debouncing to prevent unintended multiple triggers.
| LM2596 | 9V -> 5V | https://hshop.vn/mach-giamop-dc-lm2596-3a
3.3 Regulator | AMS1117 | 9V -> 5V